## Itinerary
Time | Volunteer / Lead | Activity | Items Needed
January 13-17, 2020
| Karen Mann & Committee Member | Inventory wine & spirits @ Muse | Inventory needs to be prepared in advance of the BD.
1/14/2020 noon | Emily Gray & Patti Giering | Transportation of floral containers from Marie Gossard's Shop in Oakwood to Stratacache Tower (in old muffin shop) | Floral containers
11/15/2020 11:00 AM | Emily Gray, Thom and Penni Meyer & Patti Giering | Preparation and hydration of floral stems | Stem cutters, aprons, buckets, rags, etc.
1/15/2020, following floral prep | Emily Gray, Thom and Penni Meyer & Patti Giering | Napkin folding | Napkins, storage boxes
11/15/2020 | Deven Warvel or Karen Mann | 500 Sugarfina Mint Chip candy cubes arrive at Muse via FedEx | Eight numbered orders
1/17/2020 | Emily Gray | Beer and wine delivery from Heidelberg Distributing at Stratacache Tower (store in muffin shop) | Order for wine and beer
1/17/2020 10 AM | Emily Gray, Patti Giering, Carolyn Wheeler, Sonnie Kasch | Floral arranging at Stratacache Tower (in old muffin shop) | Containers, greenery, flowers, oasis (foam), cutters, flower cages, etc.
1/17/2020 1:00 PM | Deven Warvel and Mary Campbell Zopf | Steve Mertens' session to set up flatscreen in west room of the Stratacache Tower. Load video. | Double-check that Doug sent video file to Steve.
1/17/2020 3:00 PM | Mary Campbell Zopf | Event Photographer Sarah Babcock visits Stratacache Tower to assess lighting needs. | Event photography shot list
| Muse fiscal office & development team | Prepare purchase request forms and checks for vendors who need to be paid at the BD. | Checks in hand.
| Event designer and design subcommittee | Test flower arrangements to ensure maximum visability to stage and podium. | Adjust accordingly. 2020 table tops were plastic and a bit uneven. Need to create an "tool kit" to solve problems onsite. Rosalie, will you write up your solutions.
Saturday, January 18, 2020
9:00 | Susan and Bud Zupp | Posters displayed on easels. | Posters from storage, easels
9:30 | Jennifer Leopold (Elite) Deven Warvel Pauline Fiala Patti Giering | Arrive for set-up and delivery Prime Time Rentals arrives
(see Elite invoice for complete inventory)
9:50 | Jennifer Leopold (Elite) Deven Warvel Pauline Fiala Patti Giering | Set up of tables (TBD) & chairs (TBD) | Volunteers may be called to assist with set-up.
10:00 | Jennifer Leopold (Elite) Deven Warvel Pauline Fiala Patti Giering | Registration tables (2) Place Cards | Alphabet signs, envelopes w/ tickets, pens, registration sheets, "emergency" kit, instructions, master binder
* Cocktail hour bistros (15)
|  | * Bar | Heidelberg sponsor signs (2)
* Stage
|  | * Coat Rack (6) & Hangers & Tables (2) | Tip jar, sign (Carroll Muse Club volunteers)
El Meson area tables (3)
10:15 | Pauline Fiala | BLC Entertainment Lighting & Podium
11:00 | Pauline Fiala | Monika's Sound Systems and Rentals
noon | Maria Gossard | Supervise event design
12:00 | Patti Giering & Pauline Fiala | Arrange tables, pay attention to number of seats at each table & guests. Place programs. | Table diagram, master RSVP, table numbers, programs, full place setting
12:30 | Pauline Fiala | Sound arrival and set up - Monika Shroyer
13:30 | Steve & Vicke Snyder, Sean & Teresa Sullivan, Jack Fiala | Arrive for miscellaneous tasks
13:35 | Deven Warvel & Volunteer | Step & repeat backdrop set up to the west of the stage | Move step-and-repeat backdrop (which is inside of Mary's office near office doors) to the Stratacache Tower.
14:00 | Steve Snyder | Place Benefit Dinner parking signs outside & ride with mobility van. | Jefferson Street entrance
14:00 | Sean Sullivan, Jack Fiala | Spirits are delivered.
14:00 | Jennifer Leopold | Elite Catering Staff Arrival & setup
14:00 | Jack Fiala | Heidelberg Distributing's beer & wine are moved from muffin shop to bar area.
15:00 |  | In The Heights @ the Victoria Theatre | 1 hr. and 40 min.
15:00 | Pauline Fiala | El Meson arrival, set-up & dessert delivery | Cart(s)
15:30 | Jack & Pauline Fiala | Program participants (Emcee Nate Edwards, Son Del Caribe--Gina Stough, Ovation TV/Charter Communication/Spectrum) | Program script (Ovation TV/Charter/Spectrum submitted for their portion of the evening.)
16:00 | ALL VOLUNTEERS AND STAFF DRESSED AND READY AT STRATACACHE TOWER LOBBY
16:00 | Committtee Members | Clean podium & floral containers w/cleaner, if smudged . | 2020 photos show how smudged the podium was. Bring cleaner and micro fiber clothes.
16:00 | Committee Member | Set lights w/Tower security while both guards are at the front desk. | The lights have only a few settings, but the larger hanging lights in the cocktail area need to be turned off and the dining area needs to have a few lights turned off to create a more intimate atmosphere.
16:00 | Mary Campbell Zopf & Emily Gray | Sarah Babcock photographer arrives | Shot list
16:30 | Vicke Snyder | Carroll coat check volunteers arrive (3) & receive instructions | Etiquette tips
16:45 | Deven Warvel Teresa Sullivan Karen Mann Pauline Fiala | Registration | Manifests, envelopes/tickets
17:00 | Son Del Caribe--Gina Stough | Cocktail hour begins & Son Del Caribe performs
17:30 | Steve Snyder | Mobility van from Victoria arrives
17:45 | Son Del Caribe--Gina Stough | Announcement for dinner
17:45 | Band | Guests are led to dinner via conga line (Son Del Caribe) Staff and volunteers should assist w/ this process.
17:55 | Elite, Band | Dinner served; band moves to dinner location
18:00 | Vicke Snyder | Pizza delivery for volunteers and bus driver (bar area near coat check)
Honoree Part of the Program
| 18:00 | Welcome to guests (Emcee Nat Edwards--anchor of morning show at ABC 22/FOX 45)
| 18:02 | Overview of evening (Emcee)
| 18:50 | Introduction of musical honorees: Susan and Bud Zupp (Emcee)
| 18:53 | Remarks/Tribute to honorees (Ray Zupp)
| 19:00 | Serenade honorees (Sol Del Caribe Vocalist Gina Stough)
| 19:05 | Presentation of pens to honorees( Muse Board Member Patti Giering)
| 19:10 | Transition to Ovation TV/Charter Communications/Spectrum (Emcee)
Ovation TV/Spectrum/Charter Part of the Program
| 19:03 | Introduction Muse Board President Albert Asebrook & Executive Director Mary Campbell Zopf (Emcee)
| 19:06 | Short Overview of Muse Machine (Muse Board President Albert Asebrook & Executive Director Mary Campbell Zopf)
| 19:09 | Remarks/Introduction of Ovation TV--Charter (Regional Vice-President State Government Affairs Gary Underwood, Charter Communications)
| 19:12 | Remarks/Presentation of Award--Ovation TV (Jen Kanter, Partnership Marketing Ovation TV) | Need staff person off to the west side (near Main Street) of stage with novelty check for photographs.
| 19:15 | Video/Stand for the Arts (30-second spot) | Stratacache Tower AV Support
| 19:16 | Introduction of State Rep. Fred Strahorn (Gary Underwood)
| 19:17 | Remarks/Rep. Fred Strahorn
| 7:19 | Introduction of State Representative Niraj Antani (Gary Underwood)
| 19:20 | Remarks/State Rep. Niraj Antani
| 19:22 | Closing of Award Presentation Remarks/Muse Machine (Muse Board President Albert Asebrook)
| 19:23 | Announcement of mobility van leaving and begin transition to Vic- Steve Snyder rides with van. (Emcee)
| 19:26 | Announcement for remain guests to retrieve their coats and directions for walking through the Premier Building. (Emcee)
| 19:45 | All guests arrive at the Victoria.
19:26 | Deven Warvel | Tip-jar money returned to Muse and put in safe.
19:30 | Deven Warvel, Karen Mann, Pauline & Jack Fiala, Teresa & Sean Sullivan, Vicke & Steve Snyder | Alcohol & flowers returned to Muse | Cart(s)
20:00 |  | In the Heights @ the Victoria Theatre | 1 hr. and 40 min.
19:45 | Deven Warvel, Karen Mann, Pauline & Jack Fiala, Teresa & Sean Sullivan, Vicke & Steve Snyder | Collection of centerpieces, signs and any other décor, posters & easels returned to Muse offices | Cart(s)
20:00 |  | Elite staff tears down tables & chairs
22:30 | Thom Meyer | Hold MM BD Transport sign outside the Victoria | Large sign - "MM BD Transportation"
Sunday |  | Prime Time collects tables & chairs Bud & Susan Zupp pick up posters/easels
Sunday Following the Musical
| Committee Members | Oversee the pick-up by Prime Time to ensure there was no damage or breakage during the load-out process. | 2020 Broken glass was left on the floor and the owner of Stratacache had to clean it up as he came in the building on Monday.
| Committee Members | Checks each space used for preparation and the event itself to ensure Muse is leaving it better than it found it. | 2020-- there was some confusion regarding what the clean-up team would be doing. We can definitely improve our written communication to teams who are overseeing major work area(s).
| Karen Mann & Committee Members | Transport wine & spirits back to Muse and inventory it. | Need to store in locked development office